## Product Catalog
Project Name | SportyShoes.com
StakeHolders/Customers/Users | abc/xyz/zxc etc.
Created By | Syed Fasiullah Hussaini.
Epic | User Story ID | Feature/Title | User Story | Status | Acceptance Criteria
For an admin to manage & categorize all the products, Keep track of user info. & should be able to see purchase report filtered by date & category. (SportyShoes.com_Epic_001) | US001 | Admin can change the password if he wants to. | As an Admin, I want to be able to change the password So that I can be very assured & satisfied that no one other than me can have the authority to access my E-Commerce site. | New
| US002 | Admin can manage all the products. | As an Admin, I want to be able to manage all the products that has been purchased by the user's and that are there available in my store So that I can have clear understanding of what products demands the more. | New
| US003 | Admin can categorize all the products based on brands,colors,size & price. | As an Admin, I want to be able to categorize all the products based on size, price, color & brands So that the end user can easily get the desired product within less time. | New
| US004 | Admin can browse the list of users who signed up & can be able to search users. | As an Admin, I want to be able to browse the list of users who signed up on my website so that I can search them later on, track and provide them better results in future. | New
| US005 | Admin can see purchase details of all the products filtered by date & category & also create UI side of the backend. | As an Admin, I want to be able to see the purchase details filtered by date & category So that I can maintain the list of products sold every month. | New

## Sprint Planning
Project Name | SportyShoes.com
Scrum Team | Dev, QA, PO, Scrum Master etc.
Created By | Syed Fasiullah Hussaini
Epic | User Story ID | Feature/Title | User Story | Story Points | Sprint
For an admin to manage & categorize all the products, Keep track of user info. & should be able to see purchase report filtered by date & category. | US001 | Admin can change the password if he wants to. | As an Admin, I want to be able to change the password So that I can be very assured & satisfied that no one other than me can have the authority to access my E-Commerce site. | 8 | 1
| US002 | Admin can manage all the products. | As an Admin, I want to be able to manage all the products that has been purchased by the user's and that are there available in my store So that I can have clear understanding of what products demands the more. | 3 | 1
| US003 | Admin can categorize all the products based on brands,colors,size & price. | As an Admin, I want to be able to categorize all the products based on size, price, color & brands So that the end user can easily get the desired product within less time. | 5 | 2
| US004 | Admin can browse the list of users who signed up & can be able to search users. | As an Admin, I want to be able to browse the list of users who signed up on my website so that I can search them later on, track and provide them better results in future. | 5 | 3
| US005 | Admin can see purchase details of all the products filtered by date & category. | As an Admin, I want to be able to see the purchase details filtered by date & category So that I can maintain the list of products sold every month. | 8 | 3

## Sheet1
TestCaseID | UserStoryID | Feature | User Story | Steps | Execpted Result
TC_DL_001 | US001 | Admin can manage all the products and users can search for the products based on the categories like brand ,color, size & price set by admin. | As a first-time user to the application, I want to be able to categorize all the products based on brands, colors, size & price So that the consumer can easily search for the desired product. | 1) Open postman software 2) Categorize the products. 3) Specify URI to fetch details 4) Click on Submit | User is able to see all the products based on categories.
TC_DL_002 | US002 | Admin can track all the product related details using URI or endpoint using postman tool. | As an owner of the application and admistrator of website, I want to be able to see the purchse report of all the products filtered by date & category with the help of endpoint or URI So that I can list out the products that are in demand and manufacture them. | 1) Open postman software 2) Specify URI to fetch details 3) Click on Submit | User is able to track the progress made by comparing with previous details.

## Tasks
QA Tasks | Developer Tasks
Reviewing User Stories | Reviewing User Stories
Creating Test Cases | Setting up Development Environment
Setting up Test Environment | Developing Programs
Creating Test Data | Code Review
Executing Manual Tests | Creating Unit Test Cases
Automation Setup | Executing Unt Tests
Automation Design | Merging Code
Automating Test Cases | Creating Builds
Re-Testing Bugs | Fixing Bugs